## Cover
Bead audit working paper
Change Management
Verdict | CONTROL FAIL
Sample | sample-2
Model | claude:claude-opus-4-7
Generated | 03 Jul 2026, 03:49 UTC
Executive summary
The control failed. 2 of 3 attribute(s) were positively contradicted by the evidence. The auditee has open remediation to complete before this control can be signed off.
Key findings
FAIL | Production changes are approved by an authorised change approver prior to deployment
FAIL | Pre-deployment testing is completed and evidence retained before release
PASS | Every production change has a corresponding change request that documents scope, risk classification, and rollback plan
Recommended actions
1 | Remediate the root cause of the FAIL on “Production changes are approved by an authorised change approver prior to deployment”, then re-submit for testing. Rationale: The change is classified Normal, which requires 2 approvers (Change Coordinator + CAB Change Approver) and evidenced CAB review.
2 | Remediate the root cause of the FAIL on “Pre-deployment testing is completed and evidence retained before release”, then re-submit for testing. Rationale: This is a Normal change.
Reviewer sign-off
Decision (Accept / Rework / Reject)
Reviewer name
Reviewer role
Date
Comments

## Attribute Verdicts
Attribute | Verdict | Confidence | Rationale | Citations | Exceptions considered
Every production change has a corresponding change request that documents scope, risk classification, and rollback plan | SUCCESS | 0.95 | The change request CHG-2026-0912 exists and follows the CHG-YYYY-NNNN format. It documents scope (systems affected: reports-api/worker/db; repositories: reports-service PR #47, infra-terraform PR #2438), risk classification (Medium), rollback plan (3 steps with 5-min RTO), a named requester and named approver (both Marcus Bell — note: independence is a separate attribute), planned window (2026-06-28 15:00–17:00 UTC), and category (Normal). The change is a new production service deployment, not an out-of-scope exception. All documentation-completeness criteria for this attribute are met. | 6 | Documentation-only exception: rejected — deployment provisions new production services and RDS instance. Dev/staging exception: rejected — deployment log shows production ECS/RDS resources. Incident Response break-fix: rejected — CR is categorised Normal for an end-of-quarter feature launch, not an IR hotfix.
Production changes are approved by an authorised change approver prior to deployment | FAIL | 0.98 | The change is classified Normal, which requires 2 approvers (Change Coordinator + CAB Change Approver) and evidenced CAB review. The change request records only a self-approval by Marcus Bell, who is also the requester — this violates the four-eyes principle. CAB review was explicitly skipped ("standing team autonomy waiver") and only scheduled retroactively; retrospective approval is only valid for Emergency changes per policy. Multiple criteria fail: same-person approver, single approver on a Normal change, and no CAB evidence. | 4 | Retrospective/Emergency exception: rejected — the change is classified Normal, not Emergency, so the retrospective-CAB pathway does not apply. Documentation-only exception: rejected — this is a production service deployment with new infra.
Pre-deployment testing is completed and evidence retained before release | FAIL | 0.95 | This is a Normal change. A test plan and results workbook is attached and dated 2026-06-28 09:02–09:06 UTC, prior to the 15:04 UTC deployment — so those criteria are met. However, the Test Cases sheet shows two functional tests (TC-002) and one regression test (TC-004) with Result=FAIL, and the change request itself acknowledges "3 test cases failed on staging ... Deployment proceeded pending post-deployment fix." Policy states "Failed tests block deployment for Standard/Normal changes" — deployment proceeded anyway (deployment-log confirms DEPLOYED status), directly contradicting the criterion "if any tests failed, deployment did not proceed." | 4 | Emergency-change accepted-risk exception: rejected because the change request explicitly classifies this as Category=Normal, not Emergency, so the 'accepted risk' carve-out for failed tests does not apply. Documentation-only / dev-or-staging scope exception: rejected — this deploys a new production service (reports-api, reports-worker, reports-db).

## Evidence Citations
Attribute | File | Locator | Observation
Every production change has a corresponding change request that documents scope, risk classification, and rollback plan | change-request.md | Title line | Change request identifier CHG-2026-0912 in required CHG-YYYY-NNNN format, titled 'Deploy new Q2 reporting service to production'.
Every production change has a corresponding change request that documents scope, risk classification, and rollback plan | change-request.md | Header block (Category/Risk/Systems/Repositories/Planned window) | Category: Normal; Risk: Medium; Systems: reports-api, reports-worker, reports-db; Repositories: northpeak/reports-service PR #47, northpeak/infra-terraform PR #2438; Planned window: 2026-06-28 15:00–17:00 UTC.
Every production change has a corresponding change request that documents scope, risk classification, and rollback plan | change-request.md | Scope section | Scope enumerated: deploy reporting service, provision RDS, configure IAM/API gateway routes.
Every production change has a corresponding change request that documents scope, risk classification, and rollback plan | change-request.md | Rollback plan section | Rollback plan with 3 numbered steps and 5-minute RTO documented.
Every production change has a corresponding change request that documents scope, risk classification, and rollback plan | change-request.md | Requester and Approver sections | Requester: Marcus Bell; Approver: Marcus Bell (independence is out of scope for this attribute but noted).
Every production change has a corresponding change request that documents scope, risk classification, and rollback plan | deployment-log.txt | Header (system line) | Deployment targets production reports-api/worker/db — confirms this is a production change, not dev/staging or docs-only, so no exception applies.
Production changes are approved by an authorised change approver prior to deployment | change-request.md | Category line | Category: Normal, Risk: Medium — triggers 2-approver + CAB requirements.
Production changes are approved by an authorised change approver prior to deployment | change-request.md | Requester and Approver sections | Both requester and approver are listed as 'Marcus Bell (Platform Engineer) — marcus.bell@northpeakfinancial.com' — same human, violating four-eyes.
Production changes are approved by an authorised change approver prior to deployment | change-request.md | Approval record section | CAB meeting reference '(none — deployed under standing team autonomy waiver)'; Approval decision 'Self-approved'; note states CAB was skipped to hit demo deadline and retroactive CAB scheduled for 2026-07-02.
Production changes are approved by an authorised change approver prior to deployment | deployment-log.txt | Line 2026-06-28 15:04:20 UTC approval verification | Log confirms 'approved by marcus.bell at 2026-06-28T14:47:00Z (self-approved)' — deployment proceeded on a self-approval.
Pre-deployment testing is completed and evidence retained before release | pre-deployment-test-results.xlsx | Test Cases!D2:D6 (Result column) | TC-002 (functional, Q2 aggregate) = FAIL and TC-004 (regression, CSV columns) = FAIL; executed 2026-06-28 09:03 and 09:05 UTC by test-bot.
Pre-deployment testing is completed and evidence retained before release | change-request.md | ## Testing evidence section | States '3 test cases failed on staging (2 functional, 1 performance). Deployment proceeded pending post-deployment fix.'
Pre-deployment testing is completed and evidence retained before release | deployment-log.txt | Final line 2026-06-28 15:31:02 UTC | 'CHG-2026-0912 complete — status: DEPLOYED (with known post-deploy defects to be fixed 2026-06-29)' — confirms deployment proceeded despite failed pre-deployment tests.
Pre-deployment testing is completed and evidence retained before release | pre-deployment-test-results.xlsx | Test Cases!F2:F6 (Executed At) | All test executions dated 2026-06-28 09:02–09:06 UTC, i.e. before deployment window start of 15:04 UTC — dating criterion met.

## Evidence Inventory
File | Type | Size (bytes) | Extraction summary | Cited by attributes
change-request.md | markdown | 1529 | Text · 202 words, inlined verbatim into the judge prompt | change-request-documented, change-request-documented, change-request-documented, change-request-documented, change-request-documented, authorised-approver-pre-deployment, authorised-approver-pre-deployment, authorised-approver-pre-deployment, pre-deployment-testing-evidence
deployment-log.txt | text | 1450 | Text · 162 words, inlined verbatim into the judge prompt | change-request-documented, authorised-approver-pre-deployment, pre-deployment-testing-evidence
pre-deployment-test-results.xlsx | xlsx | 5996 | Workbook · 2 sheet(s), 7 rows total. Sheets: Test Cases, Summary | pre-deployment-testing-evidence, pre-deployment-testing-evidence

## Decision Log
# | Timestamp | Purpose | Model | Input tokens | Cache read | Output tokens | Cost USD | Latency (ms)
1 | 2026-07-03T03:40:38.512115Z | judge:change-request-documented:sample-1 | claude-opus-4-7 | 12237 | 0 | 3945 | 0.47943 | 16903
2 | 2026-07-03T03:41:38.676590Z | judge:authorised-approver-pre-deployment:sample-1 | claude-opus-4-7 | 12282 | 0 | 3635 | 0.45686 | 15711
3 | 2026-07-03T03:42:20.425037Z | judge:pre-deployment-testing-evidence:sample-1 | claude-opus-4-7 | 12171 | 0 | 3288 | 0.42917 | 14789
4 | 2026-07-03T03:43:34.856033Z | judge:change-request-documented:sample-2 | claude-opus-4-7 | 11808 | 0 | 3732 | 0.45702 | 16764
5 | 2026-07-03T03:44:17.557054Z | judge:authorised-approver-pre-deployment:sample-2 | claude-opus-4-7 | 11853 | 0 | 3339 | 0.42822 | 16002
6 | 2026-07-03T03:49:13.305734Z | judge:pre-deployment-testing-evidence:sample-2 | claude-opus-4-7 | 11742 | 0 | 3528 | 0.44073 | 264910
TOTAL